## Project Planner
Team Member | Activity Description | Activity Start | Activity Duration | PERIODS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
PM | Plan Project | 1 | 2 | bar: PERIODS 1 to PERIODS 5
PM | Track Project | 3 | 3 | bar: PERIODS 3 to PERIODS 5
PM | Perform QA | 3 | 4 | bar: PERIODS 3 to PERIODS 6
SA | Prepare Primary Design | 4 | 3 | bar: PERIODS 4 to PERIODS 6
SA | Prepare Detailed Design | 6 | 1 | bar: PERIODS 6
UD | Document Design | 7 | 2 | bar: PERIODS 7 to PERIODS 8
UD | Review Design | 9 | 4 | bar: PERIODS 9 to PERIODS 12
D | Develop Software | 13 | 2 | bar: PERIODS 13 to PERIODS 14
D | Produce Hardware | 15 | 1 | bar: PERIODS 15
SA | Produce Software Packages | 16 | 1 | bar: PERIODS 16
DA | Convert User Data | 16 | 1 | bar: PERIODS 16
D | Develop User Manual | 15 | 1 | bar: PERIODS 18 to PERIODS 19
PM | Transition Management | 16 | 1 | bar: PERIODS 20 to PERIODS 23
DA | Plan Acceptance Test | 9 | 4 | bar: PERIODS 21 to PERIODS 25
T | Conduct Acceptance Test | 13 | 2 | bar: PERIODS 25 to PERIODS 26
T | Develop Test Report | 15 | 1 | bar: PERIODS 27
PM | Develop Installation Plan | 16 | 1 | bar: PERIODS 28
PM | Site Preparation | 15 | 1 | bar: PERIODS 28
PM | Install At Locations | 16 | 1 | bar: PERIODS 29
D | Hardware Maintenance | 15 | 1 | bar: PERIODS 30
D | Software Maintenance | 16 | 1 | bar: PERIODS 31

## Sheet1
Task ID | Precedence | Duration
A | - | 2
B | A | 3
C | A | 4
D | C | 3
E | B | 1
F | B, C, E | 2
G | F | 4
H | G | 2
I | H | 1
J | I | 1